Draft APPA TAG Action Plan on

Children’s Health and the Environment

- Develop awareness of indoor air pollution in APPA region

  - Educate pediatricians and other health care providers about risks of indoor air pollution

  - Raise parents awareness of how to prevent children’s exposures to indoor air pollution from indoor combustion

  - Hold a workshop in rural area to raise awareness among pediatric leaders about how to train other young pediatricians to raise awareness in pediatric training programs

  - Provide education about portable monitors that can be used by children as they go about their school and play activities

  - Provide list of available portable monitors

  - Write a summary statement that clarifies kinds of pollutants of concern in APPA region and what steps parents can take to reduce pollution in homes and schools

  - Completion date:  September 2017

- Development of a policy statement on air pollution and child health in the APPA Region

  - The APPA TAG will write a policy statement on air pollution and child health in the APPA Region

  - Completion date:  August 2017

- Write an article for the Asia Pacific Journal of Pediatrics and Child Health

  - An article on lead poisoning will be prepared and submitted to the Asia Pacific Journal of Pediatrics and Child Health

  - Completion Date:  September 2017

- Translation and Dissemination of the WHO Training Package on Children’s Environmental Health

The 20 updated WHO PowerPoint modules from the Training Package on Children’s Environmental Health will be translated into Chinese and posted on the APPA web page.

Why children? 
Children are not little adults 
Indoor air pollution 
Outdoor air pollution 
Lead

Mercury 
Pesticides 
POPs 
Water

Paediatric environmental history 
Cancer 
Food safety

Mycotoxins

Global climate change 
Injuries 
Noise

Occupational exposure

Radiation 
Respiratory diseases 
Children's Environmental Health Indicators

Completion date:  October 2016

- WHO documents on child health and the environment will be posted on the APPA web page:

Children’s Exposure to Mercury Compounds

Healthy Environments for Healthy Children

Children's Environmental Health Units

Childhood Lead Poisoning

Persistent Organic Pollutants: Impact on Child Health

Completion date:  October 2016

- Global Alliance to Eliminate Lead Paint

- The APPA TAG will participate with WHO and UNEP on the Global Alliance to Eliminate Lead Paint.

http://www.unep.org/chemicalsandwaste/Home/tabid/197/chemicalsandwaste/LeadCadmium/PrioritiesforAction/GAELP/tabid/6176/Default.aspx

- Completion date:  November 2016

- Pre Congress Workshop at 2018 Asia Pacific Congress of Pediatrics

- The APPA TAG will propose a Pre-Congress Workshop on Child Health and the Environment to be held on 22-23 August at the 2018 Asia Pacific Congress of Pediatrics in Bali.

- Completion date:  August 2018